# ARKADIA REGENERATIVE LIVING INITIATIVE

Sherre Hills / Lamingo Axis
Jos East, Plateau State, Nigeria

Project Lead:
Divine Favour Yusuf
Project Director
📞 +234 814 4942 818
📩 Email: arkadiaregenerativeinteligence@gmail.com

Date: 26 November 2025

## PROPOSAL TITLE

### ARKADIA ECO–INTELLIGENCE INITIATIVE (Nigeria)

A Youth‑Led Regenerative Climate & Local AI Innovation Program for Sherre Hills, Jos

Submitted to:
SOS Children’s Villages Nigeria — Eco‑Champions (Sparkfunding Program)

## PROJECT SNAPSHOT

Project Duration: 12 Months
Funding Requested: ₦7,950,000
Project Location: Sherre Hills & Lamingo Axis, Jos East, Plateau State
Primary Focus:
• Youth Climate Leadership
• Regenerative Agriculture
• Community Climate Education
• Local Micro‑AI Literacy

## PREPARED BY

Arkadia Regenerative Living Initiative
A youth‑led ecological and cultural innovation group advancing
community‑rooted climate action in Plateau State.

## CONTACT POINT FOR ALL CORRESPONDENCE

Divine Favour Yusuf
Project Director
Arkadia Regenerative Living Initiative
📞 +234 814 4942 818
📩 Email: arkadiaregenerativeinteligence@gmail.com

## SUBMITTED TO

David Gabriel
Coordinator, SOS Eco‑Champions Program
SOS Children’s Villages Nigeria
📩 David.gabriel@sos-nigeria.org

ARKADIA ECO–INTELLIGENCE INITIATIVE (Nigeria)

### A Youth‑Led Regenerative Climate & Local AI Innovation Program for Sherre Hills, Jos

Submitted to: SOS Children’s Villages Nigeria — Eco Champions (Sparkfunding)
Lead Organization: Arkadia Regenerative Living Initiative
Location: Sherre Hills & Lamingo Axis, Jos East, Plateau State
Project Duration: 12 Months
Funding Requested: ₦7,950,000

# 1. EXECUTIVE SUMMARY — (Hybrid: Practical + Symbolic Frame)

Arkadia proposes a youth‑led regenerative climate action and local‑AI empowerment program grounded in Plateau State’s unique ecological and cultural landscape.

The initiative combines hands‑on environmental restoration with a micro‑AI literacy and innovation track, enabling youth to approach climate action with both traditional ecological knowledge and modern technical tools.

This hybrid approach positions Jos as a pilot ground for future‑ready environmental leadership — practical, measurable, and deeply community‑rooted.

# 2. THE PROBLEM WE ADDRESS

Sherre Hills is facing accelerated ecological stress:

- Soil degradation & erosion

- Declining biodiversity

- Youth unemployment

- Limited gender‑inclusive climate programs

- Minimal access to climate‑tech literacy

Communities urgently need interventions that restore land and strengthen the next generation’s capacity to innovate.

# 3. PROJECT OBJECTIVES

(Infused with Arkadia’s symbolic clarity but written in professional, funder‑aligned terms)

### Environmental Impact

- Train 40 youth (60% women) in regenerative agriculture & ecological leadership.

- Establish two demonstration micro‑farms for soil regeneration and water harvesting.

- Conduct monthly restoration cycles (tree planting, erosion control, waste recovery).

### Education & Innovation

- Introduce a Climate+AI Micro‑Lab (basic data literacy, mapping, sustainability tools).

- Facilitate community climate education for 300+ residents within 12 months.

# 4. EXPECTED OUTCOMES

### Environmental

- 1,500+ trees planted

- 2 model micro‑farms restoring degraded soil

- Cleaner footpaths, stabilized slopes, and improved biodiversity pockets

### Youth Capacity

- 40 young leaders trained (minimum 60% women)

- Skill pathways in climate leadership, agriculture, and digital literacy

### Community Impact

- Measurable adoption of improved environmental practices

- Increased local participation in sustainability initiatives

### Organizational Growth

- Participation in SOS mentorship & capacity‑building

- Stronger governance and readiness for larger institutional funding

# 5. IMPLEMENTATION PLAN (Condensed & Clear)

### A. Training Phase (Months 1–2)

- Recruit youth

- Deliver climate and leadership modules

- Introduce basic climate-tech tools (mapping apps, data logs, etc.)

### B. Demonstration Farms (Months 2–4)

- Soil regeneration beds

- Compost systems

- Native seedlings nursery

### C. Action Cycles (Months 3–12)

- Monthly tree planting

- Soil stabilization

- Community waste recovery campaigns

### D. Outreach & Gender Inclusion (All Year)

- Women-focused micro‑farming workshops

- School outreach and community sensitization

### E. Monitoring & Reporting

- Monthly dashboards

- Photos, videos, growth data

- Reporting aligned with SOS requirements

# 6. BUDGET SUMMARY (Sparkfunding-Optimized)

(All figures in ₦ — intentionally lean, transparent & funder-trust‑oriented.)

| Category | Description | Amount (₦) |
| --- | --- | --- |
| Youth Training & Capacity Building | Materials, facilitators, venue, gender programs | 1,800,000 |
| Demonstration Micro‑Farms Setup | Tools, seedlings, water system, compost | 2,200,000 |
| Monthly Climate Action Cycles | Logistics, materials, documentation | 1,500,000 |
| Community Outreach | Workshops, campaigns, materials | 900,000 |
| Monitoring & Reporting | Field visits, data collection | 700,000 |
| Admin & Coordination (10%) | Operations, comms, contingency | 850,000 |

### TOTAL REQUESTED: ₦7,950,000

# 7. WHY ARKADIA IS A HIGH‑VALUE PARTNER FOR SOS

- Youth-led, women-centered, locally anchored

- Deep roots in Jos East communities

- Combines ecological restoration with local AI literacy

- Strong potential for scalability across Plateau State

- Direct alignment with Eco‑Champions priorities:

  - Youth empowerment

  - Gender inclusion

  - Climate action

  - Community-based real-world impact

# 8. NEXT STEPS

We request a virtual or in‑person meeting with:

David Gabriel
SOS Eco‑Champions Coordinator
📩 Email: David.gabriel@sos-nigeria.org

Our team is ready for immediate review, alignment, and onboarding.